## Study Gantt
Section | Subsection | Item ID | Item Name | Priority | Hours | Progress | Notes | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
1. Causal Inference (Primary Spike) | 1.1 Foundations | 1.1.1 | Potential Outcomes Framework (Rubin) | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.1 Foundations | 1.1.2 | Structural Causal Models (Pearl) | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.1 Foundations | 1.1.3 | Identification Strategies | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.1 | Randomized Experiments | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.2 | Difference-in-Differences (DiD) | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.3 | Regression Discontinuity (RDD) | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.4 | Instrumental Variables (IV) | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.5 | Synthetic Control Method | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.6 | Propensity Score Methods | [C] | 6 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.2 Classic Methods | 1.2.7 | Adaptive Experimentation & Bandits | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.3 Modern Causal ML | 1.3.1 | Double/Debiased Machine Learning (DML) | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.3 Modern Causal ML | 1.3.2 | Causal Forests | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.3 Modern Causal ML | 1.3.3 | Meta-Learners | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.4 Libraries & Tools | 1.4.1 | DoWhy | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.4 Libraries & Tools | 1.4.2 | EconML | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.4 Libraries & Tools | 1.4.3 | CausalML | [M] | 3 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.5 Advanced Topics | 1.5.1 | Sensitivity Analysis | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.5 Advanced Topics | 1.5.2 | Partial Identification | [L] | 2 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.5 Advanced Topics | 1.5.3 | Mediation Analysis | [M] | 3 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.6 Applications | 1.6.1 | Marketing & Uplift | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.6 Applications | 1.6.2 | Economics-Based Prediction | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
| 1.6 Applications | 1.6.3 | Supply Chain Causal Problems | [H] | 4 | 0% | [8 empty] | S | S | S | S | S | S |  |  |  |  | S
2. Probability & Statistics Foundations | 2.1 Probability Basics | 2.1.1 | Combinatorics | [M] | 3 | 0% |  |  |  | S | S | S |  | R
| 2.1 Probability Basics | 2.1.2 | Probability Rules | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.1 Probability Basics | 2.1.3 | Bayes' Theorem | [C] | 6 | 0% |  |  |  | S | S | S |  | R
| 2.2 Distributions | 2.2.1 | Discrete Distributions | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.2 Distributions | 2.2.2 | Continuous Distributions | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.2 Distributions | 2.2.3 | Key Theorems | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.3 Statistical Inference | 2.3.1 | Estimation | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.3 Statistical Inference | 2.3.2 | Hypothesis Testing | [C] | 6 | 0% |  |  |  | S | S | S |  | R
| 2.3 Statistical Inference | 2.3.3 | Common Tests | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.3 Statistical Inference | 2.3.4 | Regression Diagnostics | [H] | 4 | 0% |  |  |  | S | S | S |  | R
| 2.4 Advanced Statistical Theory | 2.4.1 | Asymptotic Theory | [M] | 3 | 0% |  |  |  | S | S | S |  | R
| 2.4 Advanced Statistical Theory | 2.4.2 | Bayesian Foundations | [M] | 3 | 0% |  |  |  | S | S | S |  | R
3. ML/DL Fundamentals | 3.1 Supervised Learning | 3.1.1 | Core Concepts | [C] | 6 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.1 Supervised Learning | 3.1.2 | Linear Models | [C] | 6 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.1 Supervised Learning | 3.1.3 | Tree-Based Methods | [C] | 6 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.1 Supervised Learning | 3.1.4 | Model Evaluation | [C] | 6 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.1 Supervised Learning | 3.1.5 | Support Vector Machines | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.1 Supervised Learning | 3.1.6 | Imbalanced Learning | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.2 Unsupervised Learning | 3.2.1 | Clustering | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.2 Unsupervised Learning | 3.2.2 | Dimensionality Reduction | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.2 Unsupervised Learning | 3.2.3 | EM Algorithm & Mixture Models | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.3 Deep Learning Basics | 3.3.1 | Neural Network Fundamentals | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.3 Deep Learning Basics | 3.3.2 | Practical Considerations | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.3 Deep Learning Basics | 3.3.3 | Architectures Overview | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.3 Deep Learning Basics | 3.3.4 | Transfer Learning | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.4 Feature Engineering | 3.4.1 | Numerical Features | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.4 Feature Engineering | 3.4.2 | Categorical Features | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.4 Feature Engineering | 3.4.3 | Missing Data | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.4 Feature Engineering | 3.4.4 | Feature Selection | [M] | 3 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.5 Model Selection & Tuning | 3.5.1 | Hyperparameter Optimization | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.5 Model Selection & Tuning | 3.5.2 | Model Comparison | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
| 3.5 Model Selection & Tuning | 3.5.3 | Model Interpretability | [H] | 4 | 0% |  |  |  |  | S | S | S | [7 empty] | S | S | S | S
4. Time Series & Forecasting | 4.1 Fundamentals | 4.1.1 | Time Series Components | [C] | 6 | 0% |  | S | S
| 4.1 Fundamentals | 4.1.2 | Stationarity | [C] | 6 | 0% |  | S | S
| 4.2 Classical Methods | 4.2.1 | ARIMA Family | [H] | 4 | 0% |  | S | S
| 4.2 Classical Methods | 4.2.2 | Exponential Smoothing | [M] | 3 | 0% |  | S | S
| 4.3 Modern Methods | 4.3.1 | Prophet | [H] | 4 | 0% |  | S | S
| 4.3 Modern Methods | 4.3.2 | ML-Based Forecasting | [H] | 4 | 0% |  | S | S
| 4.3 Modern Methods | 4.3.3 | Neural Forecasters | [M] | 3 | 0% |  | S | S
| 4.4 Practical Considerations | 4.4.1 | Evaluation Metrics | [C] | 6 | 0% |  | S | S
| 4.4 Practical Considerations | 4.4.2 | Cross-Validation for Time Series | [H] | 4 | 0% |  | S | S
| 4.4 Practical Considerations | 4.4.3 | Multiple Seasonalities | [M] | 3 | 0% |  | S | S
| 4.4 Practical Considerations | 4.4.4 | Hierarchical Forecasting | [M] | 3 | 0% |  | S | S
| 4.5 Uncertainty Quantification | 4.5.1 | Prediction Intervals | [M] | 3 | 0% |  | S | S
5. NLP, RAG & Agentic AI | 5.1 NLP Fundamentals | 5.1.1 | Text Preprocessing | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.1 NLP Fundamentals | 5.1.2 | Text Representations | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.1 NLP Fundamentals | 5.1.3 | Common Tasks | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.2 Transformers & LLMs | 5.2.1 | Transformer Architecture | [H] | 4 | 0% | [19 empty] | S | S | S
| 5.2 Transformers & LLMs | 5.2.2 | LLM Landscape | [H] | 4 | 0% | [19 empty] | S | S | S
| 5.2 Transformers & LLMs | 5.2.3 | Using LLMs | [H] | 4 | 0% | [19 empty] | S | S | S
| 5.3 RAG (Retrieval-Augmented Generation) | 5.3.1 | RAG Architecture | [H] | 4 | 0% | [19 empty] | S | S | S
| 5.3 RAG (Retrieval-Augmented Generation) | 5.3.2 | Practical Implementation | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.3 RAG (Retrieval-Augmented Generation) | 5.3.3 | RAG Evaluation | [H] | 4 | 0% | [19 empty] | S | S | S
| 5.4 Agentic AI | 5.4.1 | Agent Patterns | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.4 Agentic AI | 5.4.2 | Agent Frameworks | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.4 Agentic AI | 5.4.3 | Agent Challenges | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.5 Causal + AI Intersection | 5.5.1 | LLM Evaluation with Causal Lens | [M] | 3 | 0% | [19 empty] | S | S | S
| 5.5 Causal + AI Intersection | 5.5.2 | LLM-Assisted Causal Discovery | [M] | 3 | 0% | [19 empty] | S | S | S
6. ML System Design | 6.1 Design Patterns | 6.1.1 | Batch Prediction Systems | [H] | 4 | 0% | [24 empty] | S | S
| 6.1 Design Patterns | 6.1.2 | Real-Time Prediction Systems | [H] | 4 | 0% | [24 empty] | S | S
| 6.1 Design Patterns | 6.1.3 | Training Pipelines | [M] | 3 | 0% | [24 empty] | S | S
| 6.2 Key Components | 6.2.1 | Feature Stores | [M] | 3 | 0% | [24 empty] | S | S
| 6.2 Key Components | 6.2.2 | Model Serving | [M] | 3 | 0% | [24 empty] | S | S
| 6.2 Key Components | 6.2.3 | Monitoring & Observability | [H] | 4 | 0% | [24 empty] | S | S
| 6.2 Key Components | 6.2.4 | Data Quality & Validation | [H] | 4 | 0% | [24 empty] | S | S
| 6.2 Key Components | 6.2.5 | Feedback Loops & Bias | [H] | 4 | 0% | [24 empty] | S | S
| 6.3 Case Studies | 6.3.1 | Recommendation System | [H] | 4 | 0% | [24 empty] | S | S
| 6.3 Case Studies | 6.3.2 | Demand Forecasting System | [C] | 6 | 0% | [24 empty] | S | S
| 6.3 Case Studies | 6.3.3 | Fraud/Anomaly Detection | [M] | 3 | 0% | [24 empty] | S | S
| 6.3 Case Studies | 6.3.4 | Cold Start Strategies | [M] | 3 | 0% | [24 empty] | S | S
7. Coding & Algorithms | 7.1 Core Patterns for AS | 7.1.1 | Arrays & Hashing | [H] | 4 | 0% | [23 empty] | S |  |  | S
| 7.1 Core Patterns for AS | 7.1.2 | Trees | [H] | 4 | 0% | [23 empty] | S |  |  | S
| 7.1 Core Patterns for AS | 7.1.3 | Dynamic Programming | [H] | 4 | 0% | [23 empty] | S |  |  | S
| 7.1 Core Patterns for AS | 7.1.4 | Graphs | [M] | 3 | 0% | [23 empty] | S |  |  | S
| 7.2 Python for ML | 7.2.1 | NumPy/Pandas Proficiency | [C] | 6 | 0% | [23 empty] | S |  |  | S
| 7.2 Python for ML | 7.2.2 | Scikit-learn Fluency | [H] | 4 | 0% | [23 empty] | S |  |  | S
| 7.2 Python for ML | 7.2.3 | SQL Proficiency | [H] | 4 | 0% | [23 empty] | S |  |  | S
| 7.3 Coding Best Practices | 7.3.1 | Clean Code | [M] | 3 | 0% | [23 empty] | S |  |  | S
| 7.3 Coding Best Practices | 7.3.2 | Testing Basics | [M] | 3 | 0% | [23 empty] | S |  |  | S
8. Product Sense & Communication | 8.1 Problem Formulation | 8.1.1 | Business to Technical Translation | [C] | 6 | 0% | [27 empty] | S
| 8.1 Problem Formulation | 8.1.2 | When NOT to Use ML | [C] | 6 | 0% | [27 empty] | S
| 8.2 Stakeholder Communication | 8.2.1 | Explaining Models | [H] | 4 | 0% | [27 empty] | S
| 8.2 Stakeholder Communication | 8.2.2 | Trade-off Discussions | [H] | 4 | 0% | [27 empty] | S
| 8.3 Case Study Practice | 8.3.1 | Metric Definition Cases | [H] | 4 | 0% | [27 empty] | S
| 8.3 Case Study Practice | 8.3.2 | Ambiguous Problem Cases | [H] | 4 | 0% | [27 empty] | S
| 8.3 Case Study Practice | 8.3.3 | Trade-off Cases | [H] | 4 | 0% | [27 empty] | S
9. Breadth Topics (Low Priority) | 9.1 Markov Models | 9.1.1 | Markov Chains | [M] | 3 | 0% | [6 empty] | S | [15 empty] | S
| 9.1 Markov Models | 9.1.2 | Hidden Markov Models | [M] | 3 | 0% | [6 empty] | S | [15 empty] | S
| 9.2 Reinforcement Learning | 9.2.1 | Core Concepts Only | [L] | 2 | 0% | [6 empty] | S | [15 empty] | S
| 9.2 Reinforcement Learning | 9.2.2 | When RL is Used | [L] | 2 | 0% | [6 empty] | S | [15 empty] | S
| 9.3 Survival Analysis | 9.3.1 | Fundamentals | [M] | 3 | 0% | [6 empty] | S | [15 empty] | S
| 9.3 Survival Analysis | 9.3.2 | Methods | [M] | 3 | 0% | [6 empty] | S | [15 empty] | S
10. Optional Topics | 10.1 LLM Fine-Tuning | 10.1.1 | Fine-Tuning Approaches | [OPTIONAL] | 2 | 0%
| 10.1 LLM Fine-Tuning | 10.1.2 | Practical Fine-Tuning | [OPTIONAL] | 2 | 0%
| 10.1 LLM Fine-Tuning | 10.1.3 | Open Models | [OPTIONAL] | 2 | 0%
| 10.2 Large-Scale Processing | 10.2.1 | PySpark Basics | [OPTIONAL] | 2 | 0%
| 10.2 Large-Scale Processing | 10.2.2 | Distributed Training Concepts | [OPTIONAL] | 2 | 0%
| 10.3 Deep Framework Proficiency | 10.3.1 | PyTorch | [OPTIONAL] | 2 | 0%
| 10.3 Deep Framework Proficiency | 10.3.2 | TensorFlow/Keras | [OPTIONAL] | 2 | 0%
Project | Project 1 | P1 | Causal Uplift Modeling | - | 60 | 0% | [15 empty] | P | P | P | P
Project | Project 2 | P2 | TBD (Choose at Week 16) | - | 50 | 0% | [21 empty] | P | P | P
Mock | Mock Interview | M1 | #1 Stats + ML Fundamentals | - | 2 | 0% | [7 empty] | M
Mock | Mock Interview | M2 | #2 Causal Deep Dive | - | 2 | 0% | [13 empty] | M
Mock | Mock Interview | M3 | #3 Full Causal + ML | - | 2 | 0% | [18 empty] | M
Mock | Mock Interview | M4 | #4 GenAI + System | - | 2 | 0% | [23 empty] | M
Mock | Mock Interview | M5-8 | #5-8 Weekly Mocks | - | 8 | 0% | [24 empty] | M | M | M | M | M
Review | Final Review | R1 | Full Review Week | - | 10 | 0% | [28 empty] | R
DSA | Daily Practice | DSA | 30min daily throughout | - | 84 | 0% |  | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S

## Sheet1
1 | 365 | 365 | 1 | 0 | -3.0961 | 0.045226 | 0.95477
2 | 365 | 364 | 0.99726 | -0.0027435
3 | 365 | 363 | 0.99452 | -0.0054945
4 | 365 | 362 | 0.99178 | -0.0082531
5 | 365 | 361 | 0.98904 | -0.011019
6 | 365 | 360 | 0.9863 | -0.013793
7 | 365 | 359 | 0.98356 | -0.016575
8 | 365 | 358 | 0.98082 | -0.019364
9 | 365 | 357 | 0.97808 | -0.022162
10 | 365 | 356 | 0.97534 | -0.024967
11 | 365 | 355 | 0.9726 | -0.02778
12 | 365 | 354 | 0.96986 | -0.0306
13 | 365 | 353 | 0.96712 | -0.033429
14 | 365 | 352 | 0.96438 | -0.036266
15 | 365 | 351 | 0.96164 | -0.039111
16 | 365 | 350 | 0.9589 | -0.041964
17 | 365 | 349 | 0.95616 | -0.044825
18 | 365 | 348 | 0.95342 | -0.047695
19 | 365 | 347 | 0.95068 | -0.050573
20 | 365 | 346 | 0.94795 | -0.053459
21 | 365 | 345 | 0.94521 | -0.056353
22 | 365 | 344 | 0.94247 | -0.059256
23 | 365 | 343 | 0.93973 | -0.062167
24 | 365 | 342 | 0.93699 | -0.065087
25 | 365 | 341 | 0.93425 | -0.068015
26 | 365 | 340 | 0.93151 | -0.070952
27 | 365 | 339 | 0.92877 | -0.073897
28 | 365 | 338 | 0.92603 | -0.076851
29 | 365 | 337 | 0.92329 | -0.079814
30 | 365 | 336 | 0.92055 | -0.082786
31 | 365 | 335 | 0.91781 | -0.085767
32 | 365 | 334 | 0.91507 | -0.088756
33 | 365 | 333 | 0.91233 | -0.091755
34 | 365 | 332 | 0.90959 | -0.094762
35 | 365 | 331 | 0.90685 | -0.097779
36 | 365 | 330 | 0.90411 | -0.1008
37 | 365 | 329 | 0.90137 | -0.10384
38 | 365 | 328 | 0.89863 | -0.10688
39 | 365 | 327 | 0.89589 | -0.10994
40 | 365 | 326 | 0.89315 | -0.113
41 | 365 | 325 | 0.89041 | -0.11607
42 | 365 | 324 | 0.88767 | -0.11915
43 | 365 | 323 | 0.88493 | -0.12225
44 | 365 | 322 | 0.88219 | -0.12535
45 | 365 | 321 | 0.87945 | -0.12846
46 | 365 | 320 | 0.87671 | -0.13158
47 | 365 | 319 | 0.87397 | -0.13471

## Legend
Activity Codes
S | Study | Green
R | Review | Blue
P | Project | Orange
M | Mock Interview | Purple
Priority Colors
[C] | Critical | Red
[H] | High | Orange
[M] | Medium | Yellow
[L] | Low | Green
[OPTIONAL] | Optional | Gray

## Summary
Study Agenda Summary
Total Subsections | 121
Total Estimated Hours (topics) | 468
Project Hours | 110
DSA Hours | 84
Mock Interview Hours | 16
Review Hours | 10
Grand Total | 688
Timeline | 28 weeks
Weekly Hours | 20h
Sections by Count
Section 1: Causal Inference (Primary Spike) | 22
Section 2: Probability & Statistics Foundations | 12
Section 3: ML/DL Fundamentals | 20
Section 4: Time Series & Forecasting | 12
Section 5: NLP, RAG & Agentic AI | 14
Section 6: ML System Design | 12
Section 7: Coding & Algorithms | 9
Section 8: Product Sense & Communication | 7
Section 9: Breadth Topics (Low Priority) | 6
Section 10: Optional Topics | 7