## Gantt Chart
Section | Subsection | Priority | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28
PHASE |  |  | Phase 0 |  | Phase 1 |  |  |  |  | Phase 2 | [5 empty] | Phase 3 |  |  |  |  | Phase 4 |  |  |  |  | Phase 5
1. Causal Inference
| 1.1 Foundations | [C] | [7 empty] | S |  |  |  |  | R |  |  |  |  | R
| 1.2.1-1.2.3 A/B, DiD, RDD | [C] | [8 empty] | S |  |  |  | R
| 1.2.4-1.2.5 IV, Synthetic Control | [C] | [9 empty] | S |  |  | R
| 1.2.6-1.2.7 PSM, Bandits | [C] | [10 empty] | S |  | R
| 1.3 Modern Causal ML (DML, Meta-learners) | [H] | [11 empty] | S | [5 empty] | R
| 1.4-1.5 Libraries, Sensitivity | [H] | [12 empty] | S |  |  |  |  | R
| 1.6 Applications | [H] | [17 empty] | S
2. Stats Foundations
| 2.1 Probability | [H] |  |  | S |  |  |  | R
| 2.2-2.3 Distributions, Inference | [H] |  |  |  | S |  |  | R
| 2.4 Advanced Stats | [M] |  |  |  |  | S |  | R
3. ML/DL Fundamentals
| 3.1.1-3.1.2 Core, Linear Models | [C] |  |  |  | S |  |  | R
| 3.1.3-3.1.4 Trees, Evaluation | [C] |  |  |  |  | S |  | R
| 3.1.5-3.1.6 SVM, Imbalanced | [H] | [5 empty] | S | R
| 3.2 Unsupervised Learning | [M] | [15 empty] | S |  | R
| 3.3.1-3.3.2 NN Fundamentals | [H] | [13 empty] | S |  |  |  | R
| 3.3.3-3.3.4 Architectures, Transfer | [M] | [14 empty] | S
| 3.4 Feature Engineering | [H] | [15 empty] | S
| 3.5 Tuning, Interpretability | [H] | [16 empty] | S | R
4. Time Series
| 4.1-4.2 Fundamentals, Classical | [C] | S | S
| 4.3-4.4 Modern, Practical | [H] | S | R
| 4.5 Uncertainty | [M] |  | S
5. NLP/GenAI
| 5.1 NLP Fundamentals | [M] | [18 empty] | S
| 5.2 Transformers & LLMs | [H] | [18 empty] | S |  |  |  | R
| 5.3 RAG | [H] | [19 empty] | S |  |  | R
| 5.4-5.5 Agentic AI, Causal+AI | [M] | [20 empty] | S
6. System Design
| 6.1-6.2 Patterns, Components | [H] | [23 empty] | S |  |  |  | R
| 6.3 Case Studies | [H] | [24 empty] | S |  |  | R
7. Coding
| 7.1-7.2 Patterns, Python/SQL | [H] | [25 empty] | S |  | R
| 7.3 Best Practices | [M] | [22 empty] | S
8. Product Sense
| 8.1-8.3 Problem Formulation, Cases | [C] | [26 empty] | S | R
9. Breadth Topics
| 9.1-9.2 HMM, RL basics | [M] | [21 empty] | S
| 9.3 Survival Analysis | [M] | [5 empty] | S
ACTIVITIES
| PROJECT 1: Causal Uplift | [P] | [14 empty] | P | P | P | P
| PROJECT 2: TBD | [P] | [20 empty] | P | P | P
| DSA Practice (daily) | [D] | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D | D
| Mock Interviews | [M] | [6 empty] | M | [5 empty] | M |  |  |  |  | M |  |  |  |  | M | M | M | M | M | M
LEGEND:
S = Study | R = Review | P = Project | M = Mock Interview | D = DSA Practice

## Phase Summary
Phase | Weeks | Hours | Main Topics | Deliverables | Mock
Phase 0 | 1-2 | 40h | Time Series 4.1-4.5 | Forecasting notebook | -
Phase 1 | 3-7 | 100h | Stats 2.1-2.4, ML 3.1, Survival | XGBoost notebook, Kaplan-Meier | Week 7
Phase 2 | 8-13 | 120h | Causal 1.1-1.5 | DoWhy, EconML notebooks | Week 13
Phase 3 | 14-18 | 100h | DL 3.3, ML 3.2/3.4/3.5, PROJECT 1 | PROJECT 1 on GitHub | Week 18
Phase 4 | 19-23 | 100h | NLP 5.1-5.5, Breadth 9.1-9.2, PROJECT 2 | PROJECT 2 on GitHub | Week 23
Phase 5 | 24-28 | 100h | System Design 6, Coding 7, Product 8 | Interview readiness | Weekly